## Filers
SourceFiler | Vfiler Count | Model | S/N | DiskType | DecomBCS | Link | Status | Plan
eg-nascorp-f03 | 23 | FAS6080 | 700000422967 | FCAL 15000 RPM, 280104MB:274845MB |  |  |  | SCRAP
eg-nascorp-f04 | 16 | FAS6080 | 700000422979 | FCAL 15000 RPM, 280104MB:274845MB |  |  |  | SCRAP
eg-nasecom-e01 | 0 | FAS6080 | 700000507573 | FCAL 15000 RPM, 280104MB:274845MB | BCS46970 | https://buildcenter.thomson.com/viewproject.asp?id=BCS46970 | Submitted | SCRAP
eg-nasecom-e02 | 0 | FAS6080 | 700000507585 | FCAL 15000 RPM, 280104MB:274845MB | BCS46970 | https://buildcenter.thomson.com/viewproject.asp?id=BCS46970 | Submitted | SCRAP
eg-naslowep-h01 | 22 | FAS6210 | 800000109177 | BSAS 7200 RPM, 1695759MB
eg-naslowep-h02 | 23 | FAS6210 | 700000867832 | BSAS 7200 RPM, 1695759MB
TOTAL | 39

## Tickets
CR | EventRef | Scheduled Start | Purpose | Link | Status
CR03300977 | Audit | N/A | Audit - ISCSI | http://ereport.thomsonreuters.com/search.asp?q=CR03300977 | Complete
CR03931066 | Audit | N/A | Reclaim | http://ereport.thomsonreuters.com/search.asp?q=CR03931066 | Complete
CR09553917 | B-1054 | N/A | Prework | http://ereport.thomsonreuters.com/search.asp?q=CR09553917 | Complete
CR09553152 | B-1054-D | Jan21 04:00 GMT | NFS cutover | http://ereport.thomsonreuters.com/search.asp?q=CR09553152 | Complete
CR09903202 | B-1056 | N/A | Prework | http://ereport.thomsonreuters.com/search.asp?q=CR09903202 | Approved
CR09937251 | B-1056-D | Feb18 04:00 GMT | NFS cutover | http://ereport.thomsonreuters.com/search.asp?q=CR09937251 | Cancelled
CR09904222 | B-1056-E2 | Feb19 04:00 GMT | NFS cutover | http://ereport.thomsonreuters.com/search.asp?q=CR09904222 | Pending approval

## Summary
SourceFiler | SourcevFiler | DestinationFiler | TargetvServer | EventRef | PreworkAssignee | DFMUsed | MigrationStatus | Notes | Protocol
eg-naslowc-f01 | prod-corp-f0130 | EG-CIS-CLSP-F02-L02 | cisprod-f0152,cisprod-f0168 | B-1044-E1 | Kelsey | 7MTT | Complete | Multiprotocol VOLUME; RO/RW all entries; POSTPONED from B-1036-E2A | CIFS/NFS - MP VOL (confirmed)
Eg-naslowc-e03 | prod-corp-f0021 | EG-CIS-CLSP-F01-H03 | cisprod-f0083 | B-1056-E2 | Kelsey | 7MTT | Ready for cutover | POSTPONED from B-1029-D, B-1051-D ct_jdg_mq_nosnap rolled back | NFS
eg-naslowc-e03 | svm581unp | eg-cis-clsn-e01-l02 | cisclnt-e0096 | B-1056-E2 | Kelsey | 7MTT | Pending vserver creation |  | NFS
eg-naslowep-h01 | prod-ecom-h0061 | EG-CPS-CLSP-H01-L01 | cpsprod-h0080 | ORAARCHALT | Nirmal | 7MTT | Not Started |  | NFS
eg-naslowc-e04 | clnt-corp-e0199 | EG-CIS-CLSN-E01-L01 | DECOM | XDECOM | N/A | N/A | Complete - DECOM | CANCELLED from B-1025-B1 for DECOM | NFS

## NewVfilers
EventRef | SourceFiler | SourceVfiler | SourceIPAddress | SourceVLAN | DestinationFiler | DestVserver | DestIPAddress | DestVfilerType | Netmask | Gateway | Network | VLAN | Failover-Group | NewVserverStatus | SourceZipperInfo | AdditionalDNS
B-1051-D | eg-nascorp-f03 | prod-corp-f0021 | 10.205.120.51 | corp-3051 | EG-CIS-CLSP-F01-H03 | cisprod-f0083 | 10.205.127.46 | Generic NFS | 255.255.252.0 | 10.205.127.254 | 10.205.124.0/22 | 3051 - EAG-CORP-INFRA-VFILER-5 | data-3051 | Created | PP06802
B-1056-E2 | eg-naslowc-e03 | svm581unp | 10.204.125.199 | corp-2051 | eg-cis-clsn-e01-l02 | cisclnt-e0096 | 10.204.124.130 | Generic NFS | 255.255.252.0 | 10.204.127.254 | 10.204.124.0/22 | 2051 - EAG-CORP-INFRA-VFILER-4 | data-2051 | IP/DNS requested
B-1040-C2 | mp-naslowcc-x02 | clnt-corp-x0053 | 10.176.46.83 | corp-3051 | EG-CIS-CLSN-F02-L04 | cisclnt-f0194 | 10.205.127.160 | MP VOL | 255.255.252.0 | 10.205.127.254 | 10.205.124.0/22 | 3051 - EAG-CORP-INFRA-VFILER-5 | data-3051 | Created | BCS04345 | dev.cps-nas.int.westgroup.com

## Audit
Filer | Vfiler | TYPE | Protocol | CIFS | NFS | ISCSI | NOTES | MP VOLUMEs | DNS CNAME | VLAN
eg-naslowc-f02 | clnt-corp-f0131 | CDOT | CIFS | Yes | MIGRATED |  |  |  | westlawpzn.int.westgroup.com | 3002 - EAG-CORP-INFRA-VFILER-2
eg-naslowcc-f01 | clnt-corp-f0410 | CDOT | NFS |  | ESX |  |  |  |  | 3051 - EAG-CORP-INFRA-VFILER-5
eg-nasecom-e02 | prod-ecom-e0278 | CDOT | NFS |  | LION |  |  |  |  | 2022 - EAG-ECOM-INFRA-VFILER-1
eg-nasapp-f31 | ded-ecom-f0087 | CDOT | ISCSI |  |  | Yes |  |  |  | #3022 - EAG-ECOM-INFRA-VFILER-2
eg-naslowc-e03 | prod-corp-e0088 | 7MODE | CIFS/NFS - Separate | Yes | Yes |  |  |  |  | #2051 - EAG-CORP-INFRA-VFILER-4
eg-nasecom-e03 | prod-ecom-e0270 | CDOT | CIFS/NFS - MP VOL (confirmed) | Yes | Yes |  | MP VOLUME (per BU) | ct_datacapture_snap (MP VOLUME) | dmdsweep.westlan.com | #2022 - EAG-ECOM-INFRA-VFILER-1
eg-nascorp-f04 | prod-corp-f0101 | CDOT | NFS |  | Yes/LION |  | RO/RW all |  |  | #3002 - EAG-CORP-INFRA-VFILER-2
eg-naslowc-e03 | prod-corp-e0124 | 7MODE | CIFS | SQLARCHALT | [5 empty] | #2002 - EAG-CORP-INFRA-VFILER-1