## Summary
D&E SI Tests
NetApp SI Hardware Testing
| Results Per Section |  |  |  |  | Overall SI Results
Testing Progress | Pass | Partial | Fail | N/A | Untested | Section Complete | Overall Tests Completed (%)
Hardware Physical | 0% | 0% | 0% | 100% | 0% | 100% | 0%
Hardware Configuration | 0% | 0% | 0% | 100% | 0% | 100%
NetApp SI ONTAP Testing
| Results Per Section |  |  |  |  | Overall SI Results
Testing Progress | Pass | Partial | Fail | N/A | Untested | Section Complete | Overall Tests Completed (%)
100%
ONTAP Network | 54.55% | 0% | 0% | 45.45% | 0% | 100%
ONTAP Management | 60.87% | 0% | 0% | 39.13% | 0% | 100%
ONTAP Cluster | 71.43% | 0% | 0% | 28.57% | 0% | 100%
ONTAP NFS | 100% | 0% | 0% | 0% | 0% | 100%
ONTAP CIFS | 83.33% | 0% | 0% | 16.67% | 0% | 100%
ONTAP ISCSI | 0% | 0% | 0% | 100% | 0% | 100%
ONTAP SnapVault/SnapMirror | 60% | 30% | 0% | 10% | 0% | 100%
ONTAP Automation | 0% | 0% | 0% | 100% | 0% | 100%
ONTAP Efficiencies | 0% | 0% | 0% | 100% | 0% | 100%
ONTAP Data Recovery | 100% | 0% | 0% | 0% | 0% | 100%
NetApp SI Upgrade Testing
| Results Per Section |  |  |  |  | Overall SI Upgrade Test Results
Testing Progress | Pass | Partial | Fail | N/A | Untested | Section Complete | Overall Tests Completed (%)
ONTAP Upgrade Testing | 50% | 0% | 27.5% | 22.5% | 0% | 100% | 100%
NetApp SI OCUM Event Testing
| Results Per Section |  |  |  |  | Overall SI Upgrade Test Results
Testing Progress | Pass | Partial | Fail | N/A | Untested | Section Complete | Overall Tests Completed (%)
ONTAP OCUM Event Testing | 46.67% | 0% | 0% | 53.33% | 0% | 100% | 100%
File is to be stored in:
CONFIDENTIAL INFORMATION OF THOMSON REUTERS LIMITED This document contains information proprietary to Thomson Reuters Limited, and may not be reproduced, disclosed or used in whole or in part without the express permission of Thomson Reuters Limited. © Thomson Reuters Limited 2017

## Information
D&E Controller SI Tests
Introduction
This document specifies the SI Tests to be performed as part of the introduction of new NetApp NAS Storage. The initial tests will be carried out prior to entering into Production.
Document History
Version | Date | Author |  | Comment
1 | 2016-09-28 | Ian Daniel |  | Draft
1.1 | 2016-09-30 | Ian Daniel |  | Added service now automation tests. Added SnapVault/SnapMirror. Fixed typos. Updated Summary sheet.
1.2 | 2016-10-03 | Ian Daniel |  | Added WFA server information
1.3 | 2016-10-11 | Ian Daniel |  | Added tests provided by Architecture
1.4 | 2016-11-16 | Ian Daniel |  | Added tests for volume recovery after deletion and snapshots
1.5 | 2017-01-04 | Ian Daniel |  | Added MMC test. Updated Info.
1.6 | 2017-02-21 | Ian Daniel |  | Added OCUM Test sheet
1.7 | 2017-05-18 | Ian Daniel |  | Added Oracle Scripts as tests. Modified Upgrade Sheet Header
1.8 | 2017-05-19 | Ian Daniel |  | Added mySQL script test
1.9 | 2017-06-30 | Ian Daniel |  | Added Partial Status and updated all formulas in summary sheet
Management Overview
This document is used for initial SI testing of a new version of hardware.
Distribution List
Item | Recipient |  | Role
1
2
3
4
Glossary
Term |  |  | Definition
ASUP |  |  | Autosupport Email Notification (Call Home)
PSU |  |  | Power Supply Unit
Ops Mgr |  |  | Operations Manager
FlexVol |  |  | Flexible Volume
WAFL |  |  | Write Anywhere File Layout
ACP |  |  | Alternative Control Path
CONFIDENTIAL INFORMATION OF THOMSON REUTERS LIMITED This document contains information proprietary to Thomson Reuters Limited, and may not be reproduced, disclosed or used in whole or in part without the express permission of Thomson Reuters Limited. © Thomson Reuters Limited 2016

## Environment
Equipment Under Test
Cluster Name | System Name | Model | Serial Number | Disk Type(s) | Cards Installed | Version
orf-lab2554 | orf-lab2554-01 | FAS2554 | 701517001567 | BSAS |  | 9.1P3
| orf-lab2554-02 | FAS2554 | 701517001568 | BSAS |  | 9.1P3
AV Servers |  |  |  |  | VLAN Assignments
DNS Name | Version | IP Address | DNS Domain |  | VLAN TAG | Purpose
SI-AV-CDOT-01 | 5.8 | 10.220.177.203 | int.thomsonreuters.com |  | 2001 | Data
SI-AV-CDOT-02 | 5.8 | 10.220.177.222 | int.thomsonreuters.com |  | 2003 | Data and Inter Cluster Replication
[5 empty] | 2013 | Data and Inter Cluster Replication
DFM Server
DNS Name | Version | IP Address | DNS Domain
orf-opm-02 | 7.1P1 | 10.220.177.71 | int.thomsonreuters.com
OPM Server
DNS Name | Version | IP Address | DNS Domain
orf-opm-02 | 7.1P1 | 10.220.177.71 | int.thomsonreuters.com
WFA Server
DNS Name | Version | IP Address | DNS Domain
c239pnd | 4.0.0.0.0 | 10.252.33.3 | mgmt.tlrg.com
Grafana Server
DNS Name | Version | IP Address | DNS Domain
orf-graph-01 | 1.3 | 10.220.179.83 | int.thomsonreuters.com
Cluster IP Assignments |  |  |  | Cluster Licenses
DNS Name | IP Address | DNS Domain |  | License Feature | License Key | Expires
av-sisn01-lab01 | 10.220.181.117 | int.thomsonreuters.com |  | NFS | IDBTLVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
labsvm-e0001 | 10.220.181.53 | int.thomsonreuters.com |  | CIFS | UXYHMVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
ocum-opm-test | 10.220.181.46 | int.thomsonreuters.com |  | iSCSI | GSWWMVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
orf-lab2554 | 10.220.192.113 | int.thomsonreuters.com |  | FCP | SMULNVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
orf-lab2554-01 | 10.220.192.150 | int.thomsonreuters.com |  | SnapRestore | QBQPOVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
orf-lab2554-02 | 10.220.192.151 | int.thomsonreuters.com |  | SnapMirror | CWNEPVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
si-2554-cifs-01 | 10.220.181.121 | int.thomsonreuters.com |  | SnapVault | ALJIQVJRADDCMAAAAAAAAAAAAAAA | 7/31/2017
sicifs-e0001 | 10.220.181.90 | int.thomsonreuters.com
silab-clbk-e01 | 10.220.181.36 | int.thomsonreuters.com
silab-clbk-iscsi-01 | 10.220.181.112 10.220.181.114 10.220.181.113 (mgmt) | int.thomsonreuters.com
silab-clbk-mysql-01 | 10.220.181.56 | int.thomsonreuters.com
silab-nfscd-001 | 10.220.181.51 | int.thomsonreuters.com

## SI Hardware Testing
D&E Controller SI Tests
NetApp Checklist - Hardware Testing and Configuration |  |  | Cluster Name: | orf-lab2554 |  | CDOT Version: |  | 9.1P3
These checks are to verify that the NetApp is functioning as expected. If an error occurs make a note of it in the Notes field for the test.
Ref# | Component | Test(s) | Expected Outcome | Critical, High Risk or New Technology | Result | Verified By | Verified Date | Notes
Physical Testing
NAPHYS-001 | NetApp Build | Confirm all nodes and switches (if used) are configured as per the architecture documents. | NetApp array has been correctly commissioned | C | N/A |  |  | Previously tested prior to upgrade | Untested
NAPHYS-002 | Input Power | Check all PSUs are correctly cabled and operational | All PSUs connected and powered on. | C | N/A |  |  | Previously tested prior to upgrade | Pass
NAPHYS-003 | Standard Remote Management | Use SSH to login to all node management LIFs and the cluster management LIF. | SSH connectivity is established | C | N/A |  |  | Previously tested prior to upgrade | Fail
NAPHYS-004 | OOB Remote Management | Use SSH to connect to all node SP addresses and confirm the SP is operational | SP connectivity is established | C | N/A |  |  | Previously tested prior to upgrade | Partial
NAPHYS-005 | Autosupport | Check Autosupport is configured on all nodes (system autosupport invoke -node * -message TEST -type test) | Invoke a test ASUP on all nodes (system autosupport show -node * system autosupport history show) | C | N/A |  |  | Previously tested prior to upgrade | N/A
NAPHYS-006 | Disable autosupport for remaining tests | Disable autosupport. (system autosupport modify -node * -state disable) | Autosupport disabled (system autosupport show -node *) | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-007 | Check spare disks are available | Ensure that there are a minimum of 2 disks in the spare pool | Check with disk show -state spare | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-008 | Check shelf ACP configuration | Ensure ACP is fully operational | Check with storage shelf acp show | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-009 | MultiPath HA to Disks | Check all disks have redundant connections to controller pair | Check with node run * storage show disk –p | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-010 | Partial Power Failure (A side) | Remove one of the left hand side PSU cords from a disk tray and one from a controller | Confirm that services on both controllers are still running by using SSH on the console. Amber light on from of array should turn on and console warning should show. | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-011 | Restore Full power (A side) | Replace the removed power cords | PSU should return to service. Amber light should turn off. Console should return to status normal after a couple of minutes. | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-012 | Partial Power Failure (B side) | Do not run this test on the same disk shelf Remove one of the right hand side PSU cords from a disk tray and one from a controller | Confirm that services on both controllers are still running by using SSH on the console. Amber light on from of array should turn on and console warning should show. | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-013 | Restore Full power | Replace the removed power cord | PSU should return to service. Both the power status should be OK. | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-014 | Disk Pull | Pull out a disk that currently belongs to an aggregate and confirm spare is used. | Check for failed disk and aggregate reconstruction with aggr show -fields raidstatus | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-015 | Replace pulled disk | Reseat previously pulled disk. Check disk is added back to array as spare, but requiring to be zero’ed | Disk is re-added as a spare, but shows that it requires zero-ing | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-016 | Zero pulled disks | Zero the disk(s) | Run command “disk zerospares” Ensure disks show as zeroing using disk show -state zeroing | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-017 | Switch PSU test (If switches are used) | Remove one of the switch PSU cables | Switch remains operational. Switch status on cluster shows PSU failed. (system health cluster-switch show) | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-018 | Switch Restore Full Power (If switches are used) | Replace removed power cable | PSU returns to service and status is updated | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-019 | Cluster Interconnect Test | Identify cluster interconnect ports. Remove one of the cables from one of the nodes cluster interconnect ports. (net int show -role cluster) | Check status of cluster and interfaces. | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-020 | Mgmt port failure test | Identify port used by cluster mgmt lif and remove that cable. (net int show -role cluster-mgmt) | Cluster mgmt fails over to another node. (net int show -role cluster-mgmt) | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-021 | IFGRP Failure Test | Remove one 10GbE cable on each ifgrp and check ifgrp status. Repeat for each interface in the ifgrp | Check with ifgrp show -fields up-ports,down-ports | C | N/A |  |  | Previously tested prior to upgrade
NAPHYS-022 | Enable autosupport | Enable autosupport. (system autosupport modify -node * -state enable) | Autosupport disabled (system autosupport show -node *) | C | N/A |  |  | Previously tested prior to upgrade
Configuration Checks
NACFG-001 | License Check | Check licenses are installed | Run command "license show" and check all licenses installed are correct i.e. no Flexclone on primary cluster. | C | N/A |  |  | Previously tested prior to upgrade
NACFG-002 | Timezone | Check the timezone is correct | Run command “timezone” this should return local timezone | C | N/A |  |  | Previously tested prior to upgrade
NACFG-003 | Firmware Version | Check the version of all firmware | Run command "version -diag ". Should be running versions of ONTAP as specified in the SI test requirement plus all latest versions of BIOS and firmware. | C | N/A |  |  | Previously tested prior to upgrade
NACFG-004 | Shelf Firmware | Check the version of shelf firmware | Run command storage shelf show -fields module-fw-revision and check all shelves have current firmware installed Details available at: http://now.netapp.com | C | N/A |  |  | Previously tested prior to upgrade
NACFG-005 | ACP Firmware | Check ACP firmware on SAS shelves | Run command storage shelf acp module show -fields firmware-version and check all ACP have current firmware installed. Details available at: http://now.netapp.com | C | N/A |  |  | Previously tested prior to upgrade
NACFG-006 | Disk Firmware | Check disk firmware is up to date | Run command storage disk show -fields firmware-revision and check all disks have current firmware installed. Details available at: http://now.netapp.com | C | N/A |  |  | Previously tested prior to upgrade
NACFG-007 | RLM Firmware | Check SP firmware | Run command system service-processor show and check version of firmware installed Details available at: http://now.netapp.com | C | N/A |  |  | Previously tested prior to upgrade
NACFG-008 | Switch Firmware (If switches are used) | Connect to switches and check switch firmware is correct version | Run show version command and check firmware is at correct release. Details available at: http://now.netapp.com | C | N/A |  |  | Previously tested prior to upgrade
NACFG-009 | Switch Configuration (If switches are used) | Connect to switches and check the running config | Run show running- config command and check the config is correct. | C | N/A |  |  | Previously tested prior to upgrade
NACFG-010 | Interconnects (If switches are used) | Connect to switches and check ports are up | Run show port all command and check output | C | N/A |  |  | Previously tested prior to upgrade
NACFG-011 | Port Channel (If switches are used) | Connect to switch and check port channel configuration is correct | Run show port- channel 3/1 command and check output | C | N/A |  |  | Previously tested prior to upgrade
NACFG-012 | Check cluster MTU settings are correct | All ifgrp ports should be set to 9000 | Run net port show and check output | C | N/A |  |  | Previously tested prior to upgrade
NACFG-013 | Check IFGRPs are correct | All IFGRPs are LACP and have either 2 or 4 members in them | Run fgrp show -fields up-ports,down-ports | C | N/A |  |  | Previously tested prior to upgrade

## SI ONTAP Testing
D&E Controller SI Tests
NetApp Checklist - ONTAP Testing |  |  | Cluster Name: | orf-lab2554 |  | CDOT Version: |  | 9.1P3
These checks are to verify that the NetApp is functioning as expected. If an error occurs make a note of it in the Notes field for the test.
Ref# | Component | Test(s) | Expected Outcome | Critical, High Risk or New Technology | Result | Verified By | Verified Date | Notes
Network Testing
NANET-001 | Cluster IP Space | Check IP Spaces are configured correctly | There should be a minimum of 2 IP Spaces | N | Pass
NANET-002 | Cluster Broadcast Domain | Check Broadcast domains are correct | There should be a broadcast domain per IP Space Note: For non-management Broadcast Domains only the vlan interfaces should be present i.e. ifgrp-name-vlanid | N | Pass
NANET-003 | Cluster Broadcast Domain | Check failover groups are correct | Failover groups are correctly showing only the relevant interfaces Note: this is defined by the broadcast domains by default. | N | Pass
NANET-004 | Cluster ICLs | Create ICLs for the cluster in the relevant Broadcast domain Note: The backup cluster will need to have the same IP Spaces and broadcast domains defined in order to peer with this cluster properly. | ICLs created | C | N/A |  |  | Already done as part of 8.3.2P7 testing
NANET-005 | Cluster Peering | Create cluster peer relationship to backup cluster using correct IP address for IP Space and Broadcast Domain. | Peering successful | C | N/A |  |  | Already done as part of 8.3.2P7 testing
NANET-005 | Cluster Dual Homing | Create a second IP Space and broadcast domain for the new ifgrp | IP Space and broadcast domain created | C | N/A |  |  | Already done as part of 8.3.2P7 testing
NANET-006 | Cluster Dual Homing | Create ICLs for the cluster in the new Broadcast domain Note: The backup cluster will need to have the same IP Spaces and broadcast domains defined in order to peer with this cluster properly. | ICLs created | C | N/A |  |  | Already done as part of 8.3.2P7 testing
NANET-007 | Cluster Dual Homing | Create cluster peer relationship to backup cluster using correct IP address for new IP Space and Broadcast Domain. | Peering successful | C | N/A |  |  | Already done as part of 8.3.2P7 testing
NANET-008 | Routing | Ensure all routes are correctly added to vservers | Routes are present and a server on a different subnet can be pinged | C | Pass
NANET-009 | Generic SVM | SVM communication restrictions (DNS, LDAP, AD, domain controller) | SVM able to resolve external hosts and authentication | C | Pass |  |  |  | Untested
NANET-010 | Name Resolution | SVM must have its own DNS configuration | SVM able to resolve external hosts | C | Pass |  |  |  | Pass
Management Testing | [8 empty] | Fail
NAMGMT-001 | Cluster Management | Initiate SSH session to cluster and login | SSH session works | C | Pass |  |  |  | Partial
NAMGMT-002 | Cluster Management | Initiate telnet session to controller and login | Telnet session fails | C | Pass |  |  |  | N/A
NAMGMT-003 | Cluster Management | Initiate system manager session to controller | https://cluster-mgmt-ip system manager session works and cluster is manageable | C | Pass
NAMGMT-004 | Cluster Management | Login to OnCommand server and add controller | OCUM addition of controller succeeds | C | N/A |  |  | Already added to OCUM/OPM
NAMGMT-005 | Cluster Management | View configuration in OnCommand | OCUM shows correct cluster configuration | C | Pass
NAMGMT-006 | Cluster Management | Check controller traps are getting to OnCommand | OCUM has events for cluster and nodes | C | Pass
NAMGMT-007 | Cluster Management | Check Parser with EMAT | EMAT gets cluster events | C | N/A |  |  | Not tested in SI
NAMGMT-008 | Cluster Management | Test access to the system via SSH to each node interface using public key | Access with public key succeeds and no password required | C | Pass
NAMGMT-009 | Cluster Management | Disable SNMP v1/v2 | SNMP v1/v2 Disabled | N | Pass
NAMGMT-010 | Cluster Management | Check SNMP v3 connects and works correctly | SNMP v3 authenticated and working | N | Pass
NAMGMT-011 | Cluster Management | Test admin scripts have access to the filer via any interface and using SSH public key access. | Admin scripts run against vserver and use public key | C | Pass
NAMGMT-012 | Scripts | Check MySQL Scripts work with new version string | Script runs and selects correct OS type. | C | N/A |  |  | See upgrade tests
NAMGMT-013 | Scripts | Check Oracle Backup Script Works Against New Version of ONTAP | Script runs and selects correct OS type. DB is backed up. | C | N/A |  |  | See upgrade tests
NAMGMT-014 | Scripts | Check Oracle Flexclone Script Works Against New Version of ONTAP | Script runs and selects correct OS type. DB is recovered from backup via clones.. | C | N/A |  |  | See upgrade tests
NAMGMT-015 | Generic Management | NDU within 8.3 release | NDU process works as expected with no issues | C | N/A |  |  | Upgraded to 9.1P3 - See Upgrade tests
NAMGMT-016 | Generic Management | showmount -e improvements | Showmount works correctly when enabled on vserver | C | Pass |  |  | Disabled on vserver by default. Requested WFA workflow update 14-Jun-17
NAMGMT-017 | Generic Management | Audit log management enhancements | Enhancements perform as expected | C | Pass
NAMGMT-018 | Cluster Management | LDAP authentication for cluster management | LDAP authentication is possible to AD servers | C | N/A |  |  | Not re-tested in this SI see 8.3.2P7 docs
NAMGMT-019 | Generic Management | QOS enhancements to performance stats and workload definitions | QoS ehnacements work as expected | C | Pass
NAMGMT-020 | Generic Management | Depreciated commands (routing group) | States command deprecated or command unavailable | C | Pass |  |  | Command unavailable
NAMGMT-022 | Generic Management | Re-host a volume from one vserver to another in the same IP Space | Volume rehosted and data intact | N | N/A |  |  | See upgrade tests
NAMGMT-023 | Generic Management | Re-host a volume from one vserver to another in a different IP Space | Volume rehosted and data intact | N | N/A |  |  | See upgrade tests
NAMGMT-024 | Cluster Management | SPI Testing Browser Access | Access to https://mgmt-ip/spi successful and logs visible | C | Pass
Cluster testing
NACLUS-001 | Cluster HA | Manually initiate failover between cluster nodes. Time failover. Check the virtual names/aliases for correctness. NOTE: Ensure NFS and CIFS clients are accessing volumes during test to ensure service continuity criteria are tested properly. | vserver migrates to another node and services remain up. | C | Pass
NACLUS-002 | Cluster HA | Manually initiate giveback between cluster nodes. Time giveback and record in notes. NOTE: Ensure NFS and CIFS clients are accessing volumes during test to ensure service continuity criteria are tested properly. | vserver migrates to original node and services remain up. | C | Pass
NACLUS-003 | Cluster HA | Initiate failover by powering off one cluster node. Time failover and record in notes. NOTE: Ensure NFS and CIFS clients are accessing volumes during test to ensure service continuity criteria are tested properly. | vserver migrates to another node and services remain up. | C | Pass |  |  | 6/14/2017 22:52:00 orf-lab2554-01 EMERGENCY monitor.globalStatus.critical: This node has taken over orf-lab2554-02.
NACLUS-004 | Cluster HA | Power on the controller. | Controller starts and joins cluster. Services are resumed. | C | Pass |  |  | 6/14/2017 23:14:49 orf-lab2554-01 INFORMATIONAL sfo.giveback.complete: Giveback of SFO aggregates to partner (orf-lab2554-02) is complete. override-vetoes: false, require-partner-waiting: true, and only_newly_acquired: false.
NACLUS-005 | Cluster Networking | Power off switch NOTE: Ensure NFS and CIFS clients are accessing volumes during test to ensure service continuity criteria are tested properly. | Error is generated and cluster continues to function ASUP is generated | C | N/A |  |  | Switchless cluster
NACLUS-006 | Cluster Networking | Power on switch NOTE: Ensure NFS and CIFS c lients are accessing volumes during test to ensure service continuity criteria are tested properly. | Message generated and interconnect is restored. Cluster continues to function | C | N/A |  |  | Switchless cluster
NACLUS-007 | Cluster Networking | Test ‘vol move’ functionality and verify data can still be written to volume while move is in progress. | Vol move successful and data is written during transition | C | Pass
NFS testing
NANFS-001 | Generic NFS | Mount exported volume from vserver | Volume mounts successfully | C | Pass
NANFS-002 | Generic NFS | Mount volume from vserver onto client not in export | Mount access denied | C | Pass
NANFS-003 | Generic NFS | Write file as root onto volume exported with root access | File written | C | Pass
NANFS-004 | Generic NFS | Write file onto volume exported with no root access as root | File write fails | C | Pass
NANFS-005 | Generic NFS | Migrate data LIF used for NFS to alternate node whilst volume is mounted and files are being written NOTE: Ensure NFS clients are accessing volumes during test to ensure service continuity criteria are tested properly. | Files are written, no errors or corruption seen. | C | Pass
CIFS Testing
NACIFS-001 | Generic CIFS | Mount CIFS share from vserver | Share mounts successfully | C | Pass
NACIFS-002 | Generic CIFS | Write file as authorised user onto share | File written | C | Pass
NACIFS-003 | Generic CIFS | Write file onto share as unauthorised user | File write fails | C | Pass
NACIFS-004 | Generic CIFS | Migrate data LIF used for CIFS to alternate node whilst share is mounted and files are being written NOTE: Ensure CIFS clients are accessing volumes during test to ensure service continuity criteria are tested properly. | Files are written, no errors or corruption seen. | C | Pass
NACIFS-005 | Generic CIFS | Check CIFS shares managable via MMC | MMC can manage share permissions | N | Pass |  |  | Created a share Modified share permissions
NACIFS-006 | CIFS AV | Upgrade of connector successful if applicable | Connector upgraded | C | Pass
NACIFS-007 | CIFS AV | Create domain tunnel if none exists | Domain tunnel available | C | Pass
NACIFS-008 | CIFS AV | Create AV read only role if it does not exist. | Role available | C | N/A
NACIFS-009 | CIFS AV | Create AV Domain Account entry if none exists | Account available | C | N/A
NACIFS-010 | CIFS AV | Create AV pool if none exists | Pool available | C | N/A
NACIFS-011 | CIFS AV | Ensure AV pool is available on cluster | Pool exists | C | Pass
NACIFS-012 | CIFS AV | Associate CIFS vserver with vscan pool | Vserver associated with pool | C | Pass
NACIFS-013 | CIFS AV | Disable mandatory scanning | Mandatory scanning disabled | C | Pass
NACIFS-014 | CIFS AV | Write test virus file into share mapped to Windows server | Virus file cleaned and event generated | C | Pass |  |  | 7/4/2017 14:43:29 orf-lab2554-02 ERROR Nblade.vscanVirusDetected: Possible virus detected. Vserver: labsvm-e0005, vscan server IP: 10.220.177.203, file path: \cifs_test_01\New Text Document.txt, client IP: 10.8.40.193, SID: S-1-5-21-2012327785-2259879848-3711903672-181740, vscan engine status: 222200002, vscan engine result string: Virus Eicar_test_file Found!.
NACIFS-015 | CIFS AV | Stop AV Services on Trend server(s) | Services stopped | C | Pass
NACIFS-016 | CIFS AV | Write test virus file into share | File written to share | C | Pass
NACIFS-017 | CIFS AV | Start AV Services on Trend server(s). | Services startted | C | Pass
NACIFS-018 | CIFS AV | Access test virus file on share | File cleaned and event generated | C | Pass |  |  | 7/4/2017 14:47:53 orf-lab2554-02 ERROR Nblade.vscanVirusDetected: Possible virus detected. Vserver: labsvm-e0005, vscan server IP: 10.220.177.203, file path: \cifs_test_01\TST.txt, client IP: 10.8.40.193, SID: S-1-5-21-2012327785-2259879848-3711903672-181740, vscan engine status: 222200002, vscan engine result string: Virus Eicar_test_file Found!.
ISCSI Testing
NAISCSI-001 | Generic ISCSI | Mount LUN from vserver | Mount succeeds | C | N/A |  |  | Not in scope for this SI
NAISCSI-002 | Generic ISCSI | Mount LUN from vserver onto client not in igroup | Mount request fails | C | N/A |  |  | Not in scope for this SI
NAISCSI-003 | Generic ISCSI | Create filesystem on LUN | Filesystem created | C | N/A |  |  | Not in scope for this SI
NAISCSI-004 | Generic ISCSI | Write file onto LUN | File write succeeds | C | N/A |  |  | Not in scope for this SI
NAISCSI-005 | Generic ISCSI | Migrate volume to alternate node whilst LUN is mounted and files are being written NOTE: Ensure ISCSI clients are accessing LUNs during test to ensure service continuity criteria are tested properly. | Files are written, no errors or corruption seen.. | C | N/A |  |  | Not in scope for this SI
NAISCSI-006 | ISCSI Migration | Foreign LUN import and fast cutover | New iSCSI volume import and fast promotion capability. Prove capability works. This is not AFF specific. Re Sri may not be required at this time. | N | N/A |  |  | Not in scope for this SI
NAISCSI-007 | AFF ISCSI Migration | In-line foreign LUN import on AFF | New iSCSI volume import and fast promotion capability using all flash in-line capabilities. | N | N/A |  |  | Not in scope for this SI
SnapVault and SnapMirror Testing
NASM-001 | SnapMirror | Create secondary volume on a backup vserver | Volume created | C | Pass |  |  | Created as part of ESX workflow
NASM-002 | SnapMirror | Create vserver peer relationship if not present | Vserver peer relationship in place | C | Pass
NASM-003 | SnapMirror | Create schedule | Schedule created | C | Pass
NASM-004 | SnapMirror | Create policy on destination | Policy created | C | Pass
NASM-005 | SnapMirror | Create retention rule on destination policy | Retention rule added | C | Pass
NASM-006 | SnapMirror | Create relationship | Relationship created | C | Pass
NASM-007 | SnapMirror | Initialize relationship | Relationship initializes with no errors | C | Partial |  |  | This works in SI but it is not clear as to whether or not it is supported to SnapVault from 8.2.x to 9.1.x. FPVR is submitted but no response yet
NASM-008 | SnapMirror | Check relationship status | Status is Snapmirrored and Idle | C | Partial |  |  | This works in SI but it is not clear as to whether or not it is supported to SnapVault from 8.2.x to 9.1.x. FPVR is submitted but no response yet
NASM-009 | SnapMirror | Update relationship | Update succeeds and status reflects correct update time | C | Partial |  |  | This works in SI but it is not clear as to whether or not it is supported to SnapVault from 8.2.x to 9.1.x. FPVR is submitted but no response yet
NASM-010 | SnapMirror | Version Flexible SnapMirror test | Ensure SnapMirror to previous cDOT version is possible | C | N/A |  |  | Not offered as a feature in TR at this time
Automation Testing
NAAUTOMATION-001 | Generic Automation | Run WISP workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | N/A |  |  | See upgrade tests
NAAUTOMATION-002 | Generic Automation | Run ESX workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | N/A |  |  | See upgrade tests
NAAUTOMATION-003 | Generic Automation | Run LION workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | N/A |  |  | See upgrade tests
NAAUTOMATION-004 | Generic Automation | Run Vserver Only workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | N/A |  |  | See upgrade tests
NAAUTOMATION-005 | Service Now Automation | NAS Allocation | NAS Allocation succeeds | C | N/A |  |  | See upgrade tests
NAAUTOMATION-006 | Service Now Automation | NAS vserver Protocol Enable | Protocol enabled on Vserver | C | N/A |  |  | See upgrade tests
NAAUTOMATION-007 | Service Now Automation | NAS Volume Create | Volume created | C | N/A |  |  | See upgrade tests
NAAUTOMATION-008 | Service Now Automation | NAS Volume Deduplication Enable | DeDupe enabled | C | N/A |  |  | See upgrade tests
NAAUTOMATION-009 | Service Now Automation | NFS Export Create | NFS export rule created | C | N/A |  |  | See upgrade tests
NAAUTOMATION-010 | Service Now Automation | NFS Export Add/Remove Permissions | NFS export rule modified | C | N/A |  |  | See upgrade tests
NAAUTOMATION-011 | Service Now Automation | NAS Volume Offline/Resize/Delete | NAS volume removed | C | N/A |  |  | See upgrade tests
NAAUTOMATION-012 | Service Now Automation | NAS Qtree Create | NAS qtree created | C | N/A |  |  | See upgrade tests
NAAUTOMATION-013 | Service Now Automation | NAS Snapvault Relationship Create | SnapVault relationship created | C | N/A |  |  | See upgrade tests
NAAUTOMATION-014 | Service Now Automation | NAS Qtree Quota Resize | Quota resized | C | N/A |  |  | See upgrade tests
NAAUTOMATION-015 | Service Now Automation | NAS Snapshot Auto-Delete Enable | Snapshot autodelete enabled | C | N/A |  |  | See upgrade tests
NAAUTOMATION-016 | Service Now Automation | NAS Snapshot Enable | Snapchot enabled | C | N/A |  |  | See upgrade tests
NAAUTOMATION-017 | Service Now Automation | NAS Snapshot Create | Snapchot created | C | N/A |  |  | See upgrade tests
NAAUTOMATION-018 | Service Now Automation | NAS Snapshot Schedule Create | Snapshot schedule created | C | N/A |  |  | See upgrade tests
NAAUTOMATION-019 | Service Now Automation | NAS Snapvault Enable | SnapVault enabled | C | N/A |  |  | See upgrade tests
NAAUTOMATION-020 | Service Now Automation | NAS Snapvault Relationship Update | SnapVault relationship updated | C | N/A |  |  | See upgrade tests
NAAUTOMATION-021 | Service Now Automation | NAS Snapvault Snapshot Create | SnapVault snapshot created | C | N/A |  |  | See upgrade tests
Efficiencies
NAEFFICIENCY-001 | Compression | Compression efficiency on Oracle data. Obtain valid test data if possible and record where it came from. Record before and after values using xxx command to verify efficiency values. | 30% improvement or better | C | N/A |  |  | Tested with 8.3.2P7 - No change in functionality
NAEFFICIENCY-002 | Compression | Compression efficiency on SQL data….. as above | 30% improvement or better | C | N/A |  |  | Tested with 8.3.2P7 - No change in functionality
NAEFFICIENCY-003 | Compression | Compression efficiency on VI data….. as above | 30% improvement or better | C | N/A |  |  | Tested with 8.3.2P7 - No change in functionality
NAEFFICIENCY-004 | DeDuplication | Dedupe efficiency on Oracle data. In-line zero block….. as above | 30% improvement or better | C | N/A |  |  | Tested with 8.3.2P7 - No change in functionality
NAEFFICIENCY-005 | DeDuplication | Dedupe efficiency on SQL data….. as above | 30% improvement or better | C | N/A |  |  | Tested with 8.3.2P7 - No change in functionality
NAEFFICIENCY-006 | DeDuplication | Dedupe efficiency on VI data. In-line zero block and standard background….. as above | 30% improvement or better | C | N/A |  |  | Tested with 8.3.2P7 - No change in functionality
Data Recovery
NAREC-001 | Volume | Delete volume and check to see it is held in the deletion queue | Deleted volume is held in the queue | C | Pass
NAREC-002 | Volume | Check the following were all removed for deleted volume: QoS Policy Snapshot Policy Quotas if any | All objects deleted as expected | C | Pass
NAREC-003 | Volume | Check deleted volume has been assigned temporray name | Name is as expected: <oldname>_<DSID>' where DSID is the volume's DSID and oldname is the original volume name (truncated if this new name exceeds the max volume name length) | C | Pass |  |  | orf-lab2554::*> vol recovery-queue show Vserver Volume Deletion Request Time Retention Hours --------- ----------- ------------------------ --------------- labsvm-e0006 TEST_1176 Wed Jun 14 23:51:56 2017 12 Note: Default retention of 12 Hours might be worth increasing to a few days?
NAREC-004 | Volume | Recover volume: volume recovery-queue recover -vserver <vserver> -volume <volume> and mount it on a junction path. Export volume and check all files are there. | Volume recovered and mounted. Files are still present. | C | Pass |  |  | orf-lab2554::*> vol recovery-queue recover -vserver labsvm-e0006 -volume TEST_1176 Notice: When you bring a recovered volume online, there may be a temporary drop in performance for all volumes in the same aggregate. Volume recovery successful for volume "TEST_1176" in Vserver "labsvm-e0006".
NAREC-005 | Volume | Delete volume agaiin (NAREC-001) then purge the queue: volume recovery-queue purge -vserver <vserver> -volume <volume> | Volume destroyed and space returned to aggregate. | C | Pass |  |  | orf-lab2554::*> vol recovery-queue purge -vserver labsvm-e0006 -volume TEST_1176 Queued private job: 4724 orf-lab2554::*> orf-lab2554::*> vol recovery-queue show This table is currently empty.
NAREC-006 | Snapshot | Recover volume from snapshot copy | Volume recovered successfully | C | Pass
NAREC-007 | Snapshot | Recover a file from snapshot | File recovery successful | C | Pass

## OCUM Events
Storage Event | Management System | Event Summary | Alert Source (Element Manager) | Source Type | Critical, High Risk or New Technology | Result | Verified By | Verified Date | Notes
CFO interconnect:Down | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  | Unable to test
cfo-this-filer:cannot-takeover | OCUM 7.1P1 | SNMP Trap |  | Major | C | N/A |  |  | Unable to test
cfo-this-filer:takeover | OCUM 7.1P1 | SNMP Trap |  | Warning | C | N/A |  |  | Unable to test
sfo-interconnect:down | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  | Unable to test
sfo-interconnect:not-present | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  | Unable to test
sfo-interconnect:partial-failure | OCUM 7.1P1 | SNMP Trap |  | Warning | C | N/A |  |  | Unable to test | Untested
database-backup-failed | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  |  | Pass
global-status:critical | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  |  | Fail
host-down | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  |  | Partial
host-snmp-not-responding | OCUM 7.1P1 | SNMP Trap |  | Warning | C | N/A |  |  | SNMP no longer used | N/A
(LIF) logical-interface-status:down | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass
lun-offline | OCUM 7.1P1 | SNMP Trap |  | Warning | C | N/A |  |  | ISCSI not in scope
snapshot-full | OCUM 7.1P1 | SNMP Trap |  | Warning | C | Pass
volume-space-reserve-depleted | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  | ISCSI not in scope
Cluster Not Reachable | OCUM 7.1P1 | SNMP Trap |  | Critical | C | Pass
SVM Stopped | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass
Aggregate Offline | OCUM 7.1P1 | SNMP Trap |  | Critical | C | N/A |  |  | Unable to test
Aggregate Space Full-Primary filers | OCUM 7.1P1 | SNMP Trap | 75% | Critical | C | Pass
Aggregate Space Full-Backup filers | OCUM 7.1P1 | SNMP Trap | 85% | Critical | C | N/A
Aggregate Overcommitted | OCUM 7.1P1 | SNMP Trap | 200% | Critical | C | Pass
Inodes Full | OCUM 7.1P1 | SNMP Trap | 95% |  | C | Pass
Volume Snapshot Reserve Space Full | OCUM 7.1P1 | SNMP Trap | 95% |  | C | Pass
Inodes Nearly Full | OCUM 7.1P1 | SNMP Trap | 90% |  | C | Pass
Port Status Down | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass
Storage Failover State - Takeover | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass
Storage Failover Interconnect One or More Links Down | OCUM 7.1P1 | SNMP Trap |  |  | C | N/A
Storage Failover Not Configured | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass
Storage Failover State - Partial Giveback | OCUM 7.1P1 | SNMP Trap |  |  | C | N/A |  |  | Unable to trigger in this SI
Storage Failover Disabled | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass
Storage Failover Node Status Down | OCUM 7.1P1 | SNMP Trap |  |  | C | Pass

## SI ONTAP Upgrade Testing
D&E Controller SI Tests
NetApp Checklist - ONTAP Testing |  |  | Cluster Name: | orf-lab2554 |  | OLD CDOT Version: |  | 8.3.2P7
[6 empty] | NEW CDOT Version: |  | 9.1P3
These checks are to verify that the NetApp is functioning as expected. If an error occurs make a note of it in the Notes field for the test.
Ref# | Component | Test(s) | Expected Outcome | Critical, High Risk or New Technology | Result | Verified By | Verified Date | Notes
NAUPGD-001 | Upgrade Advisor | Run Upgrade Advisor Report For Cluster | Upgrade Advisor Report Generated | C | Pass |  |  |  | Untested
NAUPGD-002 | Pre-Upgrade | Ensure all vserver LIFs are on first node to be upgraded or add mgmt LIFs if required | All vservers have LIF on first node and/or mgmt LIFs added | C | N/A |  |  | Not a requirement for 9.1P3 upgrade | Pass
NAUPGD-003 | Pre-Upgrade | Ensure all vservers have a DNS server configured and it is reachable | DNS configured and reachable | C | Pass |  |  |  | Fail
NAUPGD-004 | Pre-Upgrade | Check auto-giveback is disabled on all nodes | Option disabled | C | Pass |  |  |  | Partial
NAUPGD-005 | ONTAP Upgrade | Perform Upgrade Steps | Upgrade succeeds and all nodes updated | C | Pass |  |  | Used ANDU Method | N/A
NAUPGD-006 | Post-Upgrade | Remove any added management LIFs | LIFs removed | C | N/A |  |  | Not a requirement for 9.1P3 upgrade, already done for 8.3.2P7
NAUPGD-007 | IP Spaces | Check only Default IP Space is present | IP Space present and all interfaces resident within it | C | N/A |  |  | More than one IP Space configure so N/A
NAUPGD-008 | Broadcast Domains | Check there is a Broadcast Domain per subnet | Broadcast domains created for all subnets that require one | C | Pass
NAUPGD-009 | Networking | Check routes are correct on vservers | All routes are in place | C | Pass
NAUPGD-010 | Client Checks | Check vservers online | Vservers all online and serving data | C | Pass
NAUPGD-011 | Client Checks | Check clients for errors | All clients working as normal (excludes CIFS) and no issues seen during upgrade. | C | Pass
NAUPGD-012 | CIFS | AV Connector Upgrade If Applicable | AV Connector upgrades with no issues and passes CIFS AV Testing | C | Pass |  |  | Connector upgraded and tested against 9.1P3 and 8.2.3P5
NAUPGD-013 | Automation | Run WISP workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | N/A |  |  | Not in scope for 9.1P3
NAUPGD-014 | Automation | Run ESX workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | Pass
NAUPGD-015 | Automation | Run LION workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | Pass
NAUPGD-016 | Automation | MySQL workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | Pass
NAUPGD-017 | Automation | Run Vserver Only workflow | Workflow completes without error and vserver is created in correct IP Space/Broadcast domain | C | Pass
NAUPGD-018 | Automation | NAS Allocation | NAS Allocation succeeds | C | Fail |  |  | 2017-07-17 20:13:04 - ICO Service Account (Work notes) The NAS Allocation process has completed UNSUCCESSFULLY. Parse NAS Allocation Request: SUCCESS Get DNS Servers: FAILURE - Result data: Unable to get information from PCM-API. AII:519
NAUPGD-019 | Automation | NAS vserver Protocol Enable | Protocol enabled on Vserver | C | Fail |  |  | All Protocols start off by stating they are not enabled. BUG On vServer: Disallowed Protocols: cifs, fcp, ndmp 2017-07-19 12:44:24 - ICO Service Account (Work notes) Unable to enable protocols on vFiler labsvm-e0010 (NasVirtualFiler ID 25950f6d00a44c519e8678da6a76cd76). Details can be found below. Error: The protocols[cifs] is already exist Process Instance ID: 2072.114853 ServiceNow RITM: RITM0042027 IM01943168 was created and assigned to MANSYS-ADE. AII:114853
NAUPGD-020 | Automation | NAS Volume Create | Volume created | C | Fail |  |  | Does not validate the volume does not already exist. BUG
NAUPGD-021 | Automation | NAS Volume Deduplication Enable | DeDupe enabled | C | Fail |  |  | Please 2017-07-18 19:54:48 - ICO Service Account (Work notes) Unable to enable deduplication on volume cb0000_si_mysql13d_s01mysql1_snap on filer orf-lab2554-02, associated with vFiler labsvm-e0010. Error: Problem while executing workflow(NAME=cDOT_NAS_Volume_Deduplication_Enable v1.0), WFA(status=Failed), Error: Unable to connect to array Process Instance ID: 2072.114830 ServiceNow RITM: RITM0041880 undefined AII:114830
NAUPGD-022 | Automation | NFS Export Create | NFS export rule created | C | N/A |  |  | DOES NOT EXIST
NAUPGD-023 | Automation | NFS Export Add/Remove Permissions | NFS export rule modified | C | N/A |  |  | DOES NOT EXIST
NAUPGD-024 | Automation | NAS Volume Offline/Resize/Delete | NAS volume removed | C | N/A |  |  | DOES NOT EXIST
NAUPGD-025 | Automation | NAS Qtree Create | NAS qtree created | C | Fail |  |  | Form does not load
NAUPGD-026 | Automation | NAS Snapvault Relationship Create | SnapVault relationship created | C | N/A |  |  | DOES NOT EXIST
NAUPGD-027 | Automation | NAS Qtree Quota Resize | Quota resized | C | N/A |  |  | DOES NOT EXIST
NAUPGD-028 | Automation | NAS Snapshot Auto-Delete Enable | Snapshot autodelete enabled | C | Fail |  |  | 2017-07-19 12:58:07 - ICO Service Account (Work notes) Unable to set AutoDelete to 'on' for volume reserve_bcs1234_cb1234_blah_2017_04_25_js Error: Problem while executing workflow(NAME=cDOT_NAS_Snapshot_AutoDelete_Enable v1.0), WFA(status=Failed), Error: Workflow aborted. No results were found. The following filters have returned empty results: Filter volumes by key Location: 'Enable snapshot autodelete settings' command > 'Volume' tab > 'volume1' variable Process Instance ID: 2072.114855 ServiceNow RITM: RITM0042028undefined AII:114855
NAUPGD-029 | Automation | NAS Snapshot Create | Snapchot created | C | Fail |  |  | 2017-07-19 13:10:42 - ICO Service Account (Work notes) Volume ID: db82bf0e047849a5bd62e3b36f81f475 Error: 500 Internal Server Error: Server Side Problem (5xx): Internal Server Error: {'Message':'Problem while executing workflow(NAME=cDOT_NAS_Snapshot_Post v1.0), WFA(status=Failed), Error: Workflow aborted. No results were found. The following filters have returned empty results: Filter volumes by key Location: 'Create volume snapshot' command > 'Volume' tab > 'volume1' variable','Action':'An Internal error occurred. Please try again. If error continues, please contact MSD support.'} InstanceID: 2072.114856 ServiceNow RITM: 14f588f51388c3849c89b53a6144b05b AII:114856
NAUPGD-030 | Automation | NAS Snapshot Schedule Create | Snapshot schedule created | C | Fail |  |  | 2017-07-19 13:18:45 - ICO Service Account (Work notes) Snapshot schedule creation failed for volume cb0000_si_mysql13d_s01mysql1_snap on vFiler labsvm-e0010. Please investigate this failure. Details can be found below. Error: Problem while executing workflow(NAME=cDOT_NAS_Snapshot_Schedule_Put v1.0), WFA(status=Failed), Error: Workflow aborted. No results were found. The following filters have returned empty results: Filter Storage Virtual Machines by key Location: 'Create or modify snapshot policy' command > 'Snapshot_Policy' tab > 'snapshot_policy1' variable > 'vserver' property Process Instance ID: 2072.114857 ServiceNow RITM: RITM0042030undefined AII:114857
NAUPGD-031 | Automation | NAS Snapvault Enable | SnapVault enabled | C | Fail |  |  | 2017-07-19 13:30:08 - ICO Service Account (Work notes) The automation process UnhandledExceptionCatcher encountered an unhandled exception. The ADE team has been notified and can be contacted (automation.dev@thomsonreuters.com) for more details. AII:114858
NAUPGD-032 | Automation | NAS Snapvault Relationship Update | SnapVault relationship updated | C | Fail |  |  | Says it is not able to find any volumes where snapshot vault is enabled
NAUPGD-033 | Automation | NAS Snapvault Snapshot Create | SnapVault snapshot created | C | Fail |  |  | 2017-07-19 13:32:49 - ICO Service Account (Work notes) Volume ID: db82bf0e047849a5bd62e3b36f81f475 Error: 500 Internal Server Error: Server Side Problem (5xx): Internal Server Error: {'Message':'Problem while executing workflow(NAME=cDOT_NAS_Snapvault_Snapshot_Post v1.0), WFA(status=Failed), Error: Workflow aborted. No results were found. The following filters have returned empty results: Filter volumes by key Location: 'Create Snapvault snapshot' command > 'Volume' tab > 'volume1' variable','Action':'An Internal error occurred. Please try again. If error continues, please contact MSD support.'} InstanceID: 2072.114859 ServiceNow RITM: ef1b487d1388c3849c89b53a6144b02a AII:114859
NAUPGD-034 | Generic Management | Re-host a volume from one vserver to another in the same IP Space | Volume rehosted and data intact | N | Pass
NAUPGD-035 | Generic Management | Re-host a volume from one vserver to another in a different IP Space | Volume rehosted and data intact | N | Pass
NAUPGD-036 | Generic Management | Disable SNMP v1/v2 | SNMP v1/v2 Disabled | N | Pass |  |  | Communities removed and SNMP v3 configured.
NAUPGD-037 | Generic Management | Check SNMP v3 connects and works correctly | SNMP v3 authenticated and working | N | Pass
NAUPGD-038 | Scripts | Check MySQL Scripts work with new version string | Script runs and selects correct OS type. | C | Pass |  |  | All scripts confirmed to work.
NAUPGD-039 | Scripts | Check Oracle Backup Script Works Against New Version of ONTAP | Script runs and selects correct OS type. DB is backed up. | C | Pass |  |  | All scripts confirmed to work.
NAUPGD-040 | Scripts | Check Oracle Flexclone Script Works Against New Version of ONTAP | Script runs and selects correct OS type. DB is recovered from backup via clones.. | C | Pass |  |  | All scripts confirmed to work.